## day_wise_plan
Daywise Plan and Course Content Mapping
Day | Module | Description | Pluralsight Course Mapping | Youtube Tutorials
1 | Project Understanding | - Understanding Project scope and requirements - Create Team/Groups - Project Allotment - Understanding Project Entities - Defining roles/responsibilities among team members - Creating DB Diagrams - Project wiring | - Git Fundamentals (02Hrs_21Mins) - Java SE Fundamentals (07Hrs) | JIRA Tutorial - https://www.youtube.com/watch?v=1RilyCsxp7U
2 | Backend Implementation | - Spring Intro - SpringBoot Intro - SpringBoot Demo - CRUD operation demo - Identifying entities by candidates as per project assigned | - Spring Framework 6 Fundamentals (02Hrs_37Mins) - SpringBoot 3 Playbook (2Hrs_17Mins) | Java Microservices Project Building - https://www.youtube.com/playlist?list=PLSVW22jAG8pBnhAdq9S8BpLnZ0_jVBj0c
3 | Backend Implementation | - Creating entites in backend logic - Configure Github Actions - Code Developmnt using CoPilot - Conneting Database entities with business logic - Understanding Microservice feature | - Java Persistence with Hibernate 5 Fundamentals (02Hrs_38Mins)
4 | Backend Implementation | - Understanding Docker basics to build images - Understanding Spring Config Server for external configuration - Environment Variables / JVM Variables - Spring Profiles - Project Business logic implementation - Project REST API Creation - Started Unit Testing - Performed CRUD Operation using SpringBoot for project by participants | - Java Microservice with SpringCloud: Developing Services (03Hrs_17Mins) - Docker for Web Developers (03hrs_45Mins) | Docker Fundamentals - https://www.youtube.com/watch?v=pTFZFxd4hOI
5 | Backend Implementation | - Understanding Edge Server - Understanding gateway server - Implementing edge and gateway server in project - Implementing communication between microservices using OpenFeign
6 | Backend Implementation | - Spring Security, Routing, Service Discovery / Registration, Inter-service communication - Understanding Observability and messaging service - Writing Tests | - Unit Testing in Spring Framework 6 with Junit (03Hrs) - Splunk 9 - Installation and Configuration (01Hrs_30Mins) | Junit Basics https://www.youtube.com/playlist?list=PLqq-6Pq4lTTa4ad5JISViSb2FVG8Vwa4o
7 | Backend Implementation | - Implementing Messaging Service and Obserability in Project - Building the docker images for project - K8s and various commands - Integrating additional features from GCP in project | - Handling streaming data with a Kafka Cluster (02Hrs_10Mins) - Building Scaleable Java Microservices with SpringBoot and SpringCloud (30Mins) | Kafka - Core Concepts https://www.youtube.com/watch?v=udnX21__SuU
8 | UI Implementation (Angular) | - Creating Components with Dummy Data - Combining components - Component Hierarchy - Writing frontend tests for components | - Angular Fundamentals (05Hrs) | Angular Concepts break-up - https://www.youtube.com/watch?v=nWst87nQmZQ&list=PLC3y8-rFHvwhBRAgFinJR8KHIrCdTkZcZ&index=12
9 | UI Implementation (Angular) | - UI Design - UI Layout - UI Logic Implementation - Writing tests using Jasmine and Karma | - Selenium 4 Fundamentals with Java (03Hrs_30Mins) | Selenium Cncepts break-up - https://www.youtube.com/playlist?list=PLL34mf651faPB-LyEP0-a7Avp_RHO0Lsm
10 | Runnable App | - Connecting BE with FE - App Deployment on GCP | - Kubernetes for Developers - Core Concepts (04Hrs_39Mins) | Kubenetes Basics https://www.youtube.com/playlist?list=PLhW3qG5bs-L8EU_Oocu6RkNPpYpaamtXX
11 | Project Demonstration | - Project Review & Evaluation

## tech_stack
Technology Stack
Stack | Technologies
Frontend | Angular v17, Bootstrap
Backend | Java, SpringBoot, Hibernate
Version Control | Git, Github
Database | RDBMS (MySQL, Postgres, h2)
DevOps | Docker, Kubernetes
Cloud | Google Cloud Platform (GCP)
Testing | Postman, Junit, Selenium
Project Management Tool | Jira